## Sheet1
STEP I (RFQ) Estimated Time Line |  |  | BOR Requirements
a. Owner issues public advertisement of RFQ | 2017-01-04 | -----
b. Deadline for written questions/requests for clarification (see Section 6). | 2017-01-13 | 4:00pm | issue addenda response at least 7 days prior to submission date (post response by the 5th due to holidays)
c. Deadline for submission of Statements of Qualifications | 2017-01-25 | 2:00pm | at least 21 days after posting date
d. Owner completes evaluation, post results, and issues notification to finalist firms | 2017-02-01 | ----- | recommended 7 day review period
e. Owner conducts Mandatory Pre-Proposal Site Visit for finalists | 2017-02-08 | TBD | at least one week after notification
f. Deadline for finalist submission of written questions and requests for clarification | 2017-02-15 | 14:00 | at least one week from site visit (allow 5 days for responses)
g. Deadline for submission of Design Team Proposals | 2017-03-01 | 14:00 | at least one week from Q&A
h. Owner interviews finalist firms and Fee Proposals are due | 2017-03-08 | TBA | at least one week from receipt of proposals